## Sheet1
| PROJECT NAME | PROJECT DURATION | PROJECT START DATE | PROJECT END DATE
| A HELPING HAND FOR THE VISUALLY CHALLENGED, MUTE AND DEAF PEOPLE | 102 | 2021-08-03 | 2021-12-02
TASK ID | TASK DESCRIPTION | TASK DURATION | START DATE | END DATE | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14
1 | Deciding on the project topic based on reseaech and study of recent trends | 6 | 2021-08-03 | 2021-08-09 | X | X | X | X | X | X | X
2 | conforming topic with faculty | 2 | 2021-08-10 | 2021-08-12 | [7 empty] | X | X | X
3 | working on problem statement for the project, deciding on project outcome and giving a detail explanation about the project | 4 | 2021-08-13 | 2021-08-17 | [10 empty] | X | X | X | X | X
4 | Planning the project and setting timeline for complition | 2 | 2021-08-18 | 2021-08-20 | [15 empty] | X | X | X
5 | Wrorking on literature review and documenting existing survey | 3 | 2021-08-21 | 2021-08-24 | [18 empty] | X | X | X | X
6 | Designing The block diagram for the project to create a basic understanding of the project | 2 | 2021-08-25 | 2021-08-27 | [22 empty] | X | X | X
7 | Working on the 1st part of the project, hand gensture recognition developing a trained model | 20 | 2021-08-28 | 2021-09-17 | [25 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
8 | Testing the model and checking how effective the model works on comand line | 5 | 2021-09-18 | 2021-09-23 | [46 empty] | X | X | X | X | X | X
9 | Start working on Braile sysytem and creating a trained machine learning model | 15 | 2021-09-24 | 2021-10-09 | [52 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
10 | Testing the model and checking how effective the model works on comand line | 3 | 2021-10-10 | 2021-10-13 | [68 empty] | X | X | X | X
11 | Working on documentation of Proposed methodology and producing detailed description of work carried out | 3 | 2021-10-14 | 2021-10-17 | [72 empty] | X | X | X | X
12 | Working on back end part of our project creating routes and functionalities | 6 | 2021-10-18 | 2021-10-24 | [76 empty] | X | X | X | X | X | X | X
13 | Working on front end part of the project and creating UI for the application | 6 | 2021-10-25 | 2021-10-31 | [83 empty] | X | X | X | X | X | X | X
14 | Documenting codes and demo will be given for the product | 2 | 2021-11-01 | 2021-11-03 | [90 empty] | X | X | X
15 | Complete project and make final alteration before deployment | 3 | 2021-11-04 | 2021-11-07 | [93 empty] | X | X | X | X
16 | Deploying product on web and start getting patent rights | 4 | 2021-11-08 | 2021-11-12 | [97 empty] | X | X | X | X | X
17 | Getting patent rights approval or succesfully sent application | 4 | 2021-11-13 | 2021-11-17 | [102 empty] | X | X | X | X | X
18 | Making a final report of all modules functonalities and documenting all works | 8 | 2021-11-18 | 2021-11-26 | [107 empty] | X | X | X | X | X | X | X | X | X
19 | Creating a poser and video for the project and submitting all documents | 2 | 2021-11-27 | 2021-11-29 | [116 empty] | X | X | X
20 | Subitting project with final report for Evaluation | 2 | 2021-11-30 | 2021-12-02 | [119 empty] | X | X | X
| Total | 102
Formulas:
PROJECT START DATE = [PROJECT END DATE, row above]+1
PROJECT END DATE = [PROJECT START DATE]+[PROJECT DURATION]